Assignment : 1

Project Title: Event Management System

Aim: Create Project Plan

Specify project name and start (or finish) date. Identify and define project tasks.

Define duration for each project task.

Define milestones in the plan Define dependency between tasks Define project calendar.

Define project resources and specify resource type

Assign resources against each task and baseline the project plan

Theory:

An Event Management System (EMS) is designed to streamline and automate the process of planning, scheduling, and managing events such as conferences, workshops, weddings, and seminars. Traditionally, event planning involves manual coordination of resources, guest lists, venues, and schedules, which can be timeconsuming and error-prone. EMS provides a digital platform where organizers can register participants, allocate resources, track budgets, and monitor progress in realtime.

The system reduces complexity by integrating modules for event creation, user registration, ticket booking, payment processing, notifications, and report generation. By centralizing all event-related data in a secure database, EMS enhances efficiency, ensures better communication, and provides a seamless experience for both organizers and attendees.

Project Plan

Project Title: Event Management System 1.

- Project Details

Project Title: Event Management System

  - Start Date: 1 Aug 2025

  - End Date: 30 Sep 2025

- Project Tasks

| Sr. No. | Task Name | Task Description | Duration (in days) |
| --- | --- | --- | --- |
| 1 | Requirement Analysis | Gather requirements from users and stakeholders | 5 |
| 2 | System Design | Design ER diagrams, DFDs, and architecture | 7 |
| 3 | Database Creation | Create database schema and relationships | 5 |
| 4 | Frontend Development | Design and develop user interface | 12 |
| 5 | Backend Development | Implement core functionalities and APIs | 12 |
| 6 | Integration | Connect frontend with backend and database | 3 |
| 7 | Documentation | Prepare final report and user manual | 4 |

- Milestones

| Milestone No. | Milestone Name | Description | Expected Date |
| --- | --- | --- | --- |
| 1 | Project initiation | Requirement and planning completed | 05-Aug-2025 |
| 2 | Design Completion | ERD, DFD, and UI designs finalized | 12-Aug-2025 |
| 3 | Development Phase | Core coding | 05-Sep-2025 |
| 4 | Testing Completed | All modules tested successfully | 20-Sep-2025 |
| 5 | Project Delivery | Final deployment and documentation | 30-Sep-2025 |

- Task Dependencies

| Task Name | Dependent On (Task Name) |
| --- | --- |
| System Design | Requirement Analysis |
| Database Creation | System Design |
| Frontend Development | System Design |
| Backend Development | Database Creation |
| Integration | Frontend Development, Backend Development |
| Testing | Integration |

| Deployment | Testing |
| --- | --- |
| Documentation | Deployment |

- Project Calendar

  - Working Days per Week: 5(Monday to Friday)

  - Working Hours per Day: 8 Hours

  - Non-working Days (if any): Saturdays,Sundays,Public Holidays

- Project Resources

| Resource Name | Resource Type (Human/Material/Tool) | Role/Use in Project |
| --- | --- | --- |
| Project Manager | Human | Planning, monitoring, reporting |
| System Analyst | Human | Requirement gathering & analysis |
| Database Designer | Human | Designing and creating database |
| Frontend Developer | Human | Developing UI/UX |
| Backend Development | Human | Coding business logic and APIs |
| Tester | Human | Testing functionalities |
| Laptop/PC | Tool | Development and testing |

| Visual Studio Code | Tool | IDE for development |
| --- | --- | --- |

- Resource Assignment to Tasks

| Task Name | Assigned Resource(s) | Estimated Effort (Hours/Days) |
| --- | --- | --- |
| Requirement Analysis | System Analyst | 40 hours |
| System Design | System Analyst, Database Designer | 56 hours |
| Database Creation | Database Designer | 40 hours |
| Frontend Development | Frontend Developer | 96 hours |
| Backend Development | Backend Developer | 96 hours |
| Integration | Frontend + Backend Developers | 40 hours |

- Baseline Plan Summary

  - Baseline Start Date: 1 Aug 2025

  - Baseline End Date: 30 Sep 2025

  - Total Estimated Duration: 60 Days

  - Total Estimated Effort: ~480 Hours

Submission Date: 1-OCT-2025

Conclusion:

The Event Management System project plan clearly defines tasks, milestones, and resources to ensure timely completion. It will help streamline event planning, improve coordination, and provide an efficient solution for managing events.