Assignment : 2

Aim: Execute and Monitor Project Plan

Update % Complete with current task status. Review the status of each task.

Compare Planned vs Actual Status Review the status of Critical Path Review resources assignation status

Project Title : Event Management System Theory: How to execute and monitor project plan?

An Event Management System (EMS) is a software solution designed to simplify and automate the process of planning, organizing, and executing events. Managing events manually often involves challenges such as miscommunication, resource conflicts, and delays. EMS addresses these issues by providing a centralized platform where tasks, schedules, and resources can be tracked in real time. The system allows event organizers to define tasks, assign responsibilities, set milestones, and monitor progress effectively.

It helps in maintaining a clear record of planned versus actual progress, ensuring that any deviations can be identified early and corrected promptly.By tracking the critical path, EMS ensures that tasks crucial to project success are closely monitored, reducing risks of delays. In addition, resource allocation is optimized by assigning the right people and tools to the right tasks, improving efficiency and productivity. EMS also supports documentation, reporting, and communication, which enhances coordination between stakeholders. Ultimately, this project provides a reliable and efficient solution for managing events of various sizes, ensuring timely completion and a smooth experience for both organizers and participants.

Project Details

| Field | Details |
| --- | --- |

| Project Title | Event Management System |
| --- | --- |
| Project Manager | Sanika Jagdale |
| Start Date | 1st August 2025 |
| Planned Finish Date | 30th September 2025 |
| Report Period | 1st August – 1st september |

- Task Progress Update

| Sr. No. | Task Name | Assigned To | Planne d Start | Planned End | % Comp let e | Actual Start | Actu al End | Remark s |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Requirement Analysis | System Analyst | 1-Aug- 2025 | 5-Aug- 2025 | 100% | 1-Aug- 2025 | 5- Aug- 2025 | Comple ted |
| 2 | System Design | Analyst & Designer | 6-Aug- 2025 | 12-Aug- 2025 | 100% | 6-Aug- 2025 | 12- Aug- 2025 | Comple ted |
| 3 | Database Creation | DB Designer | 13-Aug- 2025 | 17-Aug- 2025 | 90% | 13-Aug- 2025 | 17- Aug- 2025 | Ongoin g |
| 4 | Frontend Development | Frontend Dev | 30-Aug- 2025 | 17-Sep- 2025 | 90% | 30-Sep- 2025 | 18- Sep- 2025 | Ongoin g |
| 5 | Backend Development | Backend Dev | 30-Aug- 2025 | 17-Sep - 2025 | 85% | 30-Sep -2025 | 19- Sep - 2025 | Slightly complet e |

- Planned vs Actual Status Comparison

| Metric | Planne d | Actual | Variance / Deviation |
| --- | --- | --- | --- |
| Total Duration (Days) | 60 | 62 | +2 |
| Tasks Completed (%) | 50% | 45% | -5% |
| Milestones Achieved | 2 | 2 | On track |
| Budget Spent (if any) | $3000 | $3200 | +$200 |

- Critical Path Review

| Path No. | Task Sequence | Planned Duration | Actual Duration | On Track (Yes/No) | Delay Reason (if any) |
| --- | --- | --- | --- | --- | --- |
| 1 | Requirement  Design  DB  Backend  Integration | 45 days | 50 days | no | DB & Backend |
| 2 | Frontend  Integration  Testing  Deployment | 25 days | 25 days | yes | - |

- Resource Assignment Status :

| Resource Name | Role | Assigned Tasks | Load (%) | Availability | Remarks |
| --- | --- | --- | --- | --- | --- |
| System Analyst | Requirement & Design | Task 1,2 | 100% | Available | Completed work |
| DB designer | Database | Task 3 | 90% | Available | Minor delay |
| Frontend dev | UI | Task 4 | 85% | Available | Ongoing |
| Backend dev | Logic | Task 5 | 80% | Available | Slight delay |
| Tester | Testing | Task 6 | 0% | Available | Not started yet |

- Observations and Recommendations

  - Task Delays: Minor delays in Database and Backend development.

  - Resource Conflicts: None observed so far.

  - Suggestions for Reallocation or Rescheduling: Allocate additional support to backend development to recover lost time

  - Risks or Bottlenecks Identified: Delays in backend could push integration and testing.

  - Corrective Actions Proposed: Reassign one frontend resource part-time to assist backend until completion.

Conclusion: The monitoring of the Event Management System project shows good overall progress with most tasks on track. Minor delays in the database and backend modules have been identified, but corrective actions are planned. With continuous monitoring and proper resource allocation, the project is expected to be completed successfully within the revised timeline.