Assignment No. 3

Aim: Generate Dashboard and Reports

- Dashboard

  - Project Overview

  - Cost Overview

  - Upcoming Tasks

- Resource Reports

  - Over-allocated Resources

  - Resource Overview

- Cost Reports

  - Earned Value Report

  - Resource Cost Overview

  - Task Cost Overview

- Progress Reports

  - Critical Tasks

  - Milestone Report

  - Slipping Tasks

Theory: How to generate – Project Dashboard and Reports?

A Project Dashboard for The Event Management System provides a real-time visual summary of the app’s development status, progress, and critical metrics. To generate it, data such as completed features (e.g., video recording, GPS tracking, cloud storage sync), pending tasks (e.g., UI/UX refinement, performance optimization), deadlines, resource usage, and any risks (such as hardware compatibility or data security issues) are collected. Tools like Excel, Google Sheets, or project management software (e.g., Trello, Jira) can then be used to display this information through tables, charts, or progress indicators. The dashboard highlights key metrics such as percentage of modules completed, upcoming release milestones, and overall project progress in an easy-to-read format.

For Project Reports, information from the dashboard and developer work logs is compiled into a structured document. Reports include details of completed modules, ongoing development, issues encountered (such as video processing bugs or GPS calibration errors), resources utilized (developers, testing devices, cloud services), and time spent on each activity. These reports are generated weekly or monthly and shared with stakeholders to keep them updated. They help analyze performance, identify bottlenecks, and guide decision-making to improve efficiency and manage risks effectively, ensuring The Event Management System is delivered on time and within budget.

Project Title: Event Management System

Theory (Background / Concept of Project):

An Event Management System (EMS) is a software application designed to simplify and automate the planning, organization, and execution of events such as conferences, seminars, workshops, concerts, and festivals. Traditionally, managing events involves multiple manual tasks like maintaining guest lists, tracking payments, coordinating vendors, and preparing reports. This manual process is time-consuming, error-prone, and difficult to scale when the number of events or attendees increases.

The Event Management System provides a centralized digital platform where event organizers can:

Create and manage events with details like date, venue, and capacity.Register participants and handle ticketing/payment processes .Assign vendors and resources required for the event. Monitor attendance and generate financial/attendance reports. Use dashboards to track real-time progress and overall performance.

Project Plan:

Project Dashboard

  - Project Overview

| Project Name | Event Management System |
| --- | --- |
| Project Manager | Sanika Jagdale |
| Start Date | 1st August 2025 |
| Planned End Date | 30th September 2025 |
| Current Status | In Progress |
| % Complete | 90% |

  - Cost Overview

| Planned Budget | Actual Cost | Variance | Earned Value | Status |
| --- | --- | --- | --- | --- |
| ₹50,000 | ₹30,000 | ₹20,000 | ₹10,000 | On Track |

  - Upcoming Tasks

| Task ID | Task Name | Assigned To | Planned Start | Planned End | Status |
| --- | --- | --- | --- | --- | --- |
| 101 | Coding Implementation | sanika | 10-Sep-2025 | 16-Sep-2025 | Completed |
| 102 | Testing & Debugging | Anjali | 17-Sep-2025 | 21-Sep-2025 | In progress |
| 103 | Final Review & Deployment | Sanjana | 22-Sep-2025 | -Sep-2025 | Pending |

- Resource Reports

  - Over-Allocated Resources

| Resource Name | Role | Assigned Tasks | % Allocation | Remarks |
| --- | --- | --- | --- | --- |
| Sanika | Project Manager / Developer | All tasks | 94% | Working efficiently, monitor workload |

  - Resource Overview

| Resource Name | Type (Human/Hardware/Software) | Tasks Assigned | Load (%) | Availability |
| --- | --- | --- | --- | --- |
| Anjali | Human | All tasks | 92% | Full-time |

- Cost Reports

  - Earned Value Report

| Metric | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Cost Variance (CV) | Schedule Variance (SV) |
| --- | --- | --- | --- | --- | --- |
| Value (₹) | ₹25,000 | ₹25,000 | ₹20,000 | ₹5,000 | ₹0 |

  - Resource Cost Overview

| Resource Name | Planned Cost | Actual Cost | Variance |
| --- | --- | --- | --- |
| Anjali | ₹40,000 | ₹20,000 | ₹20,000 |

  - Task Cost Overview

| Task ID | Task Name | Planned Cost | Actual Cost | Variance |
| --- | --- | --- | --- | --- |
| 001 | Requirement Gathering | ₹6,000 | ₹5,500 | ₹500 |
| 002 | System Design | ₹6,000 | ₹5,500 | ₹500 |
| 003 | Database Setup | ₹7,000 | ₹7,000 | ₹0 |

- Progress Reports

  - Critical Tasks

| Task ID | Task Name | Assigned To | Start Date | End Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 004 | Coding Implementation | Sanjana | 10-Sep- 2025 | 16-Sep-2025 | Completed | On track |

  - Milestone Report

| Milestone ID | Milestone Name | Planned Date | Actual Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| M01 | Requirements Completed | 5-Aug-2025 | 1-Sep-2025 | Completed | On time |
| M02 | System Design Completed | 7-Aug-2025 | 8-Sep-2025 | Completed | On time |

  - Slipping Tasks

| Task ID | Task Name | Planned End | Actual End | Delay (Days) | Reason for Delay | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - | - |

Conclusion :

The is Event Management System progressing according to the planned schedule. Initial phases such as requirement gathering, system design, and core feature steps have been completed on time and within budget. Development of the remaining modules, such as cloud storage sync and crash detection, is currently in progress, and milestone reports confirm that no delays have occurred so far. Resource utilization is efficient, with Rahul managing tasks effectively. Continuous monitoring will ensure that the project is completed by the planned finish date and delivered successfully.